## 📊 Dashboard Summary
🚀 SmartShelf AI — 30-Day MVP Dashboard
Portfolio Project ¦ Next.js · NestJS · PostgreSQL · FastAPI · XGBoost ¦ Target: 30 Days
📋 PROJECT METRICS |  | 📆 WEEKLY PROGRESS |  |  | ⏱ HOURS TRACKER
📌 Total Tasks | 32 | Week | Done | Total | 📚 Planned Learn Hrs | 0
✅ Completed Tasks | 0 | Week 1 | 0 | 9 | 🔨 Planned Build Hrs | 0
🔄 In Progress | 0 | Week 2 | 0 | 7 | 📚 Actual Learn Hrs | 28
⏳ To Do | 0 | Week 3 | 0 | 7 | 🔨 Actual Build Hrs | 117.5
🚫 Blocked | 0 | Week 4 | 0 | 9 | ⚙️ Debug/Commit Hrs | 13
📊 Completion % | 0% |  |  |  | 🕐 Total Project Hrs | 158.5
ℹ️ Charts auto-refresh when tracker data is updated. Use filters on '📅 30-Day Tracker' to drill down by module, priority, or week.

## 📅 30-Day Tracker
📅 SmartShelf AI — Master 30-Day Task Tracker
ID | Week | Day | Module | Learning Topic | Learn Hrs | Build Task | Build Hrs | Subtasks | Deliverable | Acceptance Criteria | Dependency | Testing Reqd | Priority | Risk Level | Status | Blocker | Notes
1 | Week 1 | 1 | Setup & DevOps | Project structure, Git repo, Docker Compose, env setup | 1 | Init Next.js + NestJS mono-repo, Prisma setup, Neon DB connection, GitHub repo | 4 | Create Next.js app, Create NestJS app, docker-compose.yml, .env files, Prisma init | Mono-repo running locally; DB connection OK | Repo accessible, npx prisma db pull works | None | No | High | Medium | Done
2 | Week 1 | 1 | Setup & DevOps | Next.js App Router folder structure | 0.5 | Create base folder structure: /app, /components, /lib, /hooks | 0.5 | Create layout.tsx, globals.css, Tailwind config | Tailwind + ShadCN rendering in browser | npx shadcn@latest init runs clean | Task 1 | No | High | Low | Done
3 | Week 1 | 2 | Auth | JWT, Guards, RBAC in NestJS | 1.5 | NestJS AuthModule: register, login, JWT strategy, roles guard | 3.5 | auth.module.ts, jwt.strategy.ts, roles.guard.ts, auth.controller.ts, register/login DTOs | Register + Login APIs returning JWT | POST /auth/register → 201, POST /auth/login → 200 + token | Task 1 | Yes | High | Medium | Done
4 | Week 1 | 2 | Auth | Prisma User schema | 0.5 | User + Role tables in Prisma schema, run migration | 0.5 | schema.prisma: users table, run npx prisma migrate dev | Users table in DB | DB has users table, roles column | Task 1 | No | High | Low | Done
5 | Week 1 | 3 | Auth | React Hook Form + Zod validation | 1.5 | Login + Register pages in Next.js with RHF + Zod, JWT stored in httpOnly cookie or localStorage | 3.5 | login/page.tsx, register/page.tsx, authSchema.ts, useAuth hook, API client | Login flow working end-to-end | User can register, login, token stored, protected route redirects | Task 3 | Yes | High | Medium | Done
6 | Week 1 | 4 | Auth | Role-Based Access Control | 1 | Admin vs Staff role UI, protect routes and API endpoints | 4 | middleware.ts for route protection, RolesGuard on NestJS controllers, admin-only pages | Admin sees all menus, Staff sees limited menus | Admin can access /admin, Staff gets 403 on admin routes | Task 3 | Yes | High | Medium | Done
7 | Week 1 | 5 | Products | Prisma schema — categories, products | 1 | NestJS CategoriesModule and ProductsModule: CRUD APIs | 4 | categories table, products table in schema.prisma, migrate, category CRUD endpoints | GET/POST /categories, GET/POST/PUT/DELETE /products work | All 4 CRUD operations return correct status codes | Task 4 | Yes | High | Medium | Done
8 | Week 1 | 6 | Products | ShadCN table, forms, dialogs | 1 | Product list page, add/edit dialog with RHF+Zod, category filter | 4 | products/page.tsx, ProductTable, AddProductDialog, EditProductDialog | Products list renders, add/edit/delete from UI works | Product count updates on add, edit reflects in table | Task 7 | Yes | High | Low | Done
9 | Week 1 | 7 | Products | Buffer/review day | 0.5 | Fix bugs, write unit tests for auth and products, review Week 1 | 2.5 | jest unit tests for AuthService, ProductsService | Passing unit tests | Jest reports 0 failures for auth + products | Tasks 3-8 | Yes | Medium | Low | Done
10 | Week 2 | 8 | Vendors | Prisma vendors table, NestJS VendorsModule | 1 | Vendor CRUD APIs, vendor list + add/edit UI pages | 4 | vendors table, VendorsModule, VendorsController, VendorService | GET/POST/PUT/DELETE /vendors work | Vendor appears in list after add | Task 1 | Yes | High | Low | Done
11 | Week 2 | 9 | Purchases | Purchase orders schema + API | 1.5 | NestJS PurchasesModule: create PO, auto-increment stock via stock_movements | 3.5 | purchase_orders, purchase_order_items, stock_movements tables; PurchasesController | POST /purchases creates PO and increments product stock | Stock quantity increases after purchase | Task 10 | Yes | High | High | Done
12 | Week 2 | 10 | Purchases | Purchase entry UI | 0.5 | Purchase entry form: select vendor, add line items, submit | 4.5 | purchases/new/page.tsx, PurchaseForm, VendorSelect, LineItems component | User can create a purchase bill from UI | Stock quantity updates visible on product page | Task 11 | Yes | High | Medium | In Progress
13 | Week 2 | 11 | Sales | Sales/Billing schema + API | 1.5 | NestJS SalesModule: create sale, auto-decrement stock, block if insufficient | 3.5 | sales, sale_items tables; SalesController with stock check | POST /sales creates sale and decrements stock | Stock decreases; returns 400 if stock insufficient | Task 12 | Yes | High | High | To Do
14 | Week 2 | 12 | Sales | Sales billing UI | 0.5 | Sales bill UI: product search, quantity, auto-total, submit | 4.5 | sales/new/page.tsx, BillingForm, ProductSearch, BillSummary | User can create sale from UI | Bill total correct, stock decreases | Task 13 | Yes | High | Medium | To Do
15 | Week 2 | 13 | Alerts | Low-stock + expiry alert logic | 1.5 | Alert API: query products below threshold and near expiry; notification bar in UI | 3.5 | AlertsController, alert queries in ProductsService; AlertBanner component | Alert shows when stock < threshold or expiry < 7 days | Low-stock banner appears; expiry badge on product | Task 12 | Yes | High | High | To Do
16 | Week 2 | 14 | Inventory | product_batches for expiry tracking | 1 | Batch tracking: each purchase creates a batch with expiry_date | 3 | product_batches table, batch expiry logic in PurchasesService, FEFO stock deduction | Expiry dates stored per batch | Batch expiry visible in product detail | Task 11 | Yes | High | Medium | To Do
17 | Week 3 | 15 | Dashboard | Recharts, NestJS dashboard API | 1.5 | Dashboard API: total sales, revenue, low-stock count, top products; Next.js dashboard page | 3.5 | DashboardController, dashboard aggregation queries; dashboard/page.tsx, metric cards | Dashboard cards show real data | Revenue card matches sum of sales | Task 13 | Yes | High | Medium | To Do
18 | Week 3 | 16 | Dashboard | Recharts charts: bar + line | 0.5 | Weekly sales trend (line chart), top 5 products (bar chart) using Recharts | 4.5 | SalesTrendChart.tsx, TopProductsChart.tsx | Both charts render with real data | Chart X-axis = dates, Y-axis = revenue | Task 17 | Yes | High | Low | To Do
19 | Week 3 | 17 | Reports | CSV export API + download button | 1 | NestJS ReportsModule: generate CSV for sales, inventory; Next.js download button | 4 | ReportsController, csv-writer or plain string CSV; ReportPage download button | CSV downloads with correct data | Opened CSV has headers + correct rows | Task 13 | Yes | High | Low | To Do
20 | Week 3 | 18 | ML Service | FastAPI setup + data preprocessing | 1.5 | FastAPI app, /health endpoint, load Online Retail dataset, feature engineering with Pandas | 3.5 | main.py, preprocess.py, requirements.txt, Dockerfile for ML service | FastAPI /health returns 200 | curl /health → {status: ok} | Task 1 | No | High | Medium | To Do
21 | Week 3 | 19 | ML Service | XGBoost model train + save | 1.5 | Train XGBoost regressor on synthetic/retail dataset, save with joblib, /train endpoint | 3.5 | train.py, model.pkl, /train POST endpoint | Model trains and saves | model.pkl exists after /train call | Task 20 | No | High | High | To Do
22 | Week 3 | 20 | ML Service | Forecast API + NestJS integration | 1 | FastAPI /forecast endpoint; NestJS ForecastModule calls ML service; UI forecast card | 4 | forecast.py, /forecast endpoint; ForecastController in NestJS; ForecastCard.tsx | NestJS calls ML service; forecast appears in UI | POST /forecast returns predicted qty for next 7 days | Task 21 | Yes | High | High | To Do
23 | Week 3 | 21 | ML Service | Fallback rule-based forecast | 0.5 | If ML service down: use 7-day rolling average as fallback in NestJS | 2.5 | fallback-forecast.service.ts using avg of last 7 days stock movements | Fallback forecast works when ML is off | Disable ML service → fallback values appear | Task 22 | No | Medium | Low | To Do
24 | Week 4 | 22 | Testing | Jest unit tests | 1 | Unit tests for AuthService, ProductsService, SalesService, ForecastService | 4 | *.spec.ts for each service; npm run test | All unit tests pass | jest --coverage shows 70%+ on services | Task 9 | Yes | High | Low | To Do
25 | Week 4 | 23 | Testing | Supertest API integration tests | 1 | API tests for auth, products, purchases, sales endpoints with Supertest | 4 | app.e2e-spec.ts or separate spec files; npm run test:e2e | All API tests pass | 200/201 on valid requests, 400/401 on invalid | Task 24 | Yes | High | Medium | To Do
26 | Week 4 | 24 | Testing | Playwright E2E tests | 1 | E2E: register, login, add product, create sale, verify stock, check alerts | 4 | tests/e2e/*.spec.ts with Playwright; npx playwright test | All 8 E2E test scenarios pass | Playwright report shows 0 failures | Task 25 | Yes | High | Medium | To Do
27 | Week 4 | 25 | Deployment | Neon DB + backend deploy on Render/Railway | 1 | Deploy NestJS to Render/Railway with Neon PostgreSQL, set env vars, run migrations | 4 | Render/Railway service config, DATABASE_URL pointing to Neon, prisma migrate deploy | Backend live at public URL | GET /health returns 200 on production URL | Task 1 | No | High | High | To Do
28 | Week 4 | 26 | Deployment | ML Service Docker deploy on Render | 0.5 | Dockerize FastAPI ML service, push to Render as Docker service | 4.5 | Dockerfile for ML, render.yaml or manual setup, ML_SERVICE_URL env in NestJS | ML service live at public URL | POST /forecast returns data from production URL | Task 27 | No | High | High | To Do
29 | Week 4 | 27 | Deployment | Frontend deploy on Vercel | 0.5 | Deploy Next.js to Vercel, set NEXT_PUBLIC_API_URL, test all pages | 4.5 | Vercel project config, env vars, production build passes | Frontend live at vercel.app URL | All pages load without console errors | Task 28 | No | High | Medium | To Do
30 | Week 4 | 28 | Portfolio | README, screenshots, seed data | 1 | Write professional README.md, add screenshots, create seed script with demo data | 4 | README.md with badges, screenshots/, seed.ts prisma seeder, demo credentials | README complete with screenshots | GitHub README renders correctly with images | Task 29 | No | High | Low | To Do
31 | Week 4 | 29 | Portfolio | Demo video recording | 0.5 | Record 3-5 min Loom/OBS demo video: login → products → sale → dashboard → forecast | 2.5 | demo.mp4 or Loom link in README | Demo video uploaded and linked | Link in README opens video | Task 30 | No | Medium | Low | To Do
32 | Week 4 | 30 | Portfolio | Final review + buffer | 1 | Final bug fixes, update portfolio site, LinkedIn post, submit to portfolio | 4 | All issues closed on GitHub, portfolio site updated | All deployment URLs live and working | Live URLs accessible; no critical bugs | All | No | High | Low | To Do
TOTAL |  |  |  |  | 31 |  | 114

## 📆 Weekly Overview
📆 SmartShelf AI — Weekly Milestones & Hours Overview
Week 1: Foundation + Auth + Products ¦ Days 1–7 (Jul 1–7)
Learn Hrs | 6 | Build Hrs | 23 | Total Hrs | 29 | Learn + Build / Day | 4.1 | Milestone | Auth system + product management live
KEY DELIVERABLES & MILESTONE CHECKLIST
✅ Mono-repo with Next.js + NestJS running locally
✅ Docker Compose + Neon PostgreSQL connection
✅ JWT register/login APIs with guards
✅ RBAC: Admin vs Staff roles working
✅ Product + Category CRUD (API + UI)
✅ Passing unit tests for auth and products
Week 2: Inventory Core — Vendors, Purchases, Sales, Alerts ¦ Days 8–14 (Jul 8–14)
Learn Hrs | 7 | Build Hrs | 26.5 | Total Hrs | 33.5 | Learn + Build / Day | 4.8 | Milestone | Full inventory in/out cycle working end-to-end
KEY DELIVERABLES & MILESTONE CHECKLIST
✅ Vendor CRUD (API + UI)
✅ Purchase entry: creates PO + increments stock
✅ Sales billing: creates sale + decrements stock
✅ Low-stock alert banner
✅ Expiry alert with batch tracking
✅ Stock movement audit trail
Week 3: Dashboard + Reports + ML Forecast Service ¦ Days 15–21 (Jul 15–21)
Learn Hrs | 7 | Build Hrs | 25.5 | Total Hrs | 32.5 | Learn + Build / Day | 4.6 | Milestone | End-to-end data flow from DB → ML → UI
KEY DELIVERABLES & MILESTONE CHECKLIST
✅ Dashboard cards (revenue, sales, low-stock count)
✅ Recharts: weekly sales trend + top products chart
✅ CSV report download
✅ FastAPI ML service running
✅ XGBoost model trained and saved
✅ Forecast API integrated in UI + rule-based fallback
Week 4: Testing + Deployment + Portfolio Polish ¦ Days 22–30 (Jul 22–30)
Learn Hrs | 6 | Build Hrs | 32.5 | Total Hrs | 38.5 | Learn + Build / Day | 5.5 | Milestone | Fully deployed, tested, portfolio-ready MVP
KEY DELIVERABLES & MILESTONE CHECKLIST
✅ Jest unit tests (70%+ coverage on services)
✅ Supertest API integration tests
✅ Playwright E2E tests (8 scenarios)
✅ NestJS live on Render/Railway + Neon DB
✅ FastAPI ML service on Render Docker
✅ Next.js live on Vercel
✅ README + screenshots + demo video

## 📚 Learning Plan
📚 SmartShelf AI — Structured Learning Plan
Day | Tech Topic | Focus Area | Resource / Official Docs | Est. Hrs | Completed? | Notes
1 | TypeScript Fundamentals | Types, interfaces, generics, utility types | https://www.typescriptlang.org/docs/ | 1 | Yes
1 | Project Structure | Next.js App Router, NestJS modular arch | https://nextjs.org/docs/app | 1 | Yes
2 | NestJS Core | Modules, Controllers, Services, DI pattern | https://docs.nestjs.com/ | 1
2 | JWT Authentication | Access tokens, refresh tokens, guards | https://docs.nestjs.com/security/authentication | 0.5
3 | React Hook Form | useForm, Controller, FormProvider | https://react-hook-form.com/docs | 0.75
3 | Zod Validation | Schema definition, .parse, .safeParse | https://zod.dev/ | 0.75
4 | RBAC Patterns | Roles, Permissions, Guards in NestJS | https://docs.nestjs.com/guards | 1
5 | Prisma ORM | Schema, relations, migrations, queries | https://www.prisma.io/docs | 1
5 | PostgreSQL Relations | FK, joins, indexes, EXPLAIN ANALYZE | https://www.postgresql.org/docs/ | 0.5
6 | ShadCN UI | Components: Table, Dialog, Form, Badge | https://ui.shadcn.com/docs | 0.5
6 | Tailwind CSS | Responsive utilities, dark mode | https://tailwindcss.com/docs | 0.5
8 | Prisma Relations | One-to-many, many-to-many patterns | https://www.prisma.io/docs/orm/prisma-schema/data-model/relations | 0.5
9 | Stock Movement Logic | FIFO/FEFO batch deduction patterns | https://docs.nestjs.com/techniques/database | 1
10 | NestJS Pipes | ValidationPipe, custom pipes, DTOs | https://docs.nestjs.com/pipes | 0.5
13 | Alert Patterns | Scheduled tasks, Cron in NestJS | https://docs.nestjs.com/techniques/task-scheduling | 1
15 | Recharts | LineChart, BarChart, ResponsiveContainer | https://recharts.org/en-US/api | 0.75
15 | NestJS Aggregation | GroupBy, sum, count with Prisma | https://www.prisma.io/docs/orm/prisma-client/queries/aggregation-grouping-summarizing | 0.75
18 | FastAPI Basics | Routes, Pydantic models, async endpoints | https://fastapi.tiangolo.com/ | 1
18 | Pandas Feature Engineering | Lag features, rolling mean, date features | https://pandas.pydata.org/docs/user_guide/ | 0.5
19 | XGBoost Regression | DMatrix, XGBRegressor, hyperparams | https://xgboost.readthedocs.io/ | 1
19 | joblib Model Persistence | dump, load, pipeline saving | https://joblib.readthedocs.io/ | 0.5
20 | Online Retail Dataset | UCI dataset structure, preprocessing steps | https://archive.ics.uci.edu/dataset/352/online+retail | 0.5
22 | Jest Testing | describe, it, expect, mocks, spies | https://jestjs.io/docs/getting-started | 1
23 | Supertest API Testing | HTTP assertions with NestJS test module | https://docs.nestjs.com/fundamentals/testing | 1
24 | Playwright E2E | page.goto, fill, click, expect | https://playwright.dev/docs/intro | 1
25 | Render/Railway Deployment | Service config, env vars, auto-deploy | https://render.com/docs | 0.5
26 | Docker for ML | Dockerfile, multi-stage, render docker | https://docs.docker.com/get-started/ | 0.5
27 | Vercel Deployment | Project settings, env vars, preview URLs | https://vercel.com/docs | 0.5

## 🛠 Tech Stack
🛠 SmartShelf AI — Tech Stack & Official Documentation
Layer | Technology | Version | Purpose | Why Used in This Project | Official Docs URL | Notes
Frontend | Next.js | 15 (App Router) | React framework | App Router for SSR/RSC, file-based routing, Vercel deployment | https://nextjs.org/docs/app
Frontend | TypeScript | 5.x | Type safety | Catch bugs at compile-time across FE+BE | https://www.typescriptlang.org/docs/
Frontend | Tailwind CSS | 3.x | Utility CSS | Rapid styling without custom CSS files | https://tailwindcss.com/docs
Frontend | ShadCN UI | latest | Component library | Accessible, copy-paste components built on Radix UI | https://ui.shadcn.com/docs
Frontend | React Hook Form | 7.x | Form management | Minimal re-renders, native HTML form integration | https://react-hook-form.com/docs
Frontend | Zod | 3.x | Schema validation | Runtime validation + TypeScript inference from one schema | https://zod.dev/
Frontend | Recharts | 2.x | Data visualization | React-native charts, composable, works with Tailwind | https://recharts.org/en-US/api
Backend | NestJS | 10.x | Node.js framework | Modular, DI, decorators — production-grade structure | https://docs.nestjs.com/
Backend | TypeScript | 5.x | Type safety | Same lang across FE+BE reduces context switching | https://www.typescriptlang.org/docs/
Backend | JWT | jsonwebtoken | Authentication | Stateless auth, scalable, industry standard | https://docs.nestjs.com/security/authentication
Backend | Passport.js | jwt strategy | Auth middleware | NestJS passport integration for JWT strategy | http://www.passportjs.org/
Database | PostgreSQL | 15.x | Relational DB | ACID transactions, strong relations for inventory | https://www.postgresql.org/docs/
Database | Prisma ORM | 5.x | DB client | Type-safe queries, migrations, schema-first approach | https://www.prisma.io/docs
Database | Neon PostgreSQL | cloud | Managed DB | Serverless Postgres, free tier, Vercel-friendly | https://neon.tech/docs/introduction
ML Service | Python | 3.11 | ML language | Rich ecosystem: pandas, sklearn, xgboost | https://docs.python.org/3/
ML Service | FastAPI | 0.100+ | ML API server | Async, auto OpenAPI docs, Pydantic validation | https://fastapi.tiangolo.com/
ML Service | Pandas | 2.x | Data processing | DataFrame ops, feature engineering, date manipulation | https://pandas.pydata.org/docs/user_guide/
ML Service | Scikit-learn | 1.3+ | ML utilities | Preprocessing, train/test split, metrics | https://scikit-learn.org/stable/
ML Service | XGBoost | 2.x | Demand forecast model | Gradient boosting, handles tabular retail data well | https://xgboost.readthedocs.io/
ML Service | joblib | latest | Model persistence | Efficient serialization of sklearn/xgboost models | https://joblib.readthedocs.io/
ML Data | Online Retail Dataset | UCI | Training data | Real retail transaction data for model training | https://archive.ics.uci.edu/dataset/352/online+retail | UCI ML Repository
Testing | Jest | 29.x | Unit testing | NestJS default test runner, great mocking support | https://jestjs.io/docs/getting-started
Testing | Supertest | 6.x | API testing | HTTP assertions for NestJS E2E tests | https://docs.nestjs.com/fundamentals/testing
Testing | Playwright | latest | E2E browser tests | Cross-browser, auto-wait, great for UI flows | https://playwright.dev/docs/intro
DevOps | Docker | 24.x | Containerization | ML service containerized for consistent deployment | https://docs.docker.com/get-started/
DevOps | Docker Compose | 3.x | Local multi-service | Run all services locally with single command | https://docs.docker.com/compose/
Deployment | Vercel | cloud | Frontend hosting | Zero-config Next.js deploy, edge network | https://vercel.com/docs
Deployment | Render/Railway | cloud | Backend hosting | Easy Node.js + Docker deploys, free tier | https://render.com/docs
Deployment | GitHub Actions | optional | CI/CD pipeline | Automated test runs on push (optional for MVP) | https://docs.github.com/en/actions | Optional Week 4

## 🗄 DB Schema
🗄 SmartShelf AI — PostgreSQL Database Schema Plan (Prisma)
Table Name | Purpose | Important Fields | Relations | MVP Required | Notes
users | Authentication & user management | id (uuid), email, password_hash, role (ADMIN¦STAFF), is_active, created_at | shops via shop_members | Yes | Seed with 1 admin + 1 staff user
shops | Shop/store profile | id, name, address, phone, currency, timezone, owner_id | owner → users; shop_members | Yes | Single shop for MVP
shop_members | Many-to-many: user ↔ shop | id, user_id, shop_id, role, created_at | users, shops | Yes | Enables multi-shop future
categories | Product categories | id, name, description, shop_id, created_at | products | Yes
products | Product catalog | id, name, sku, barcode, category_id, unit, reorder_level, selling_price, shop_id, created_at | categories, product_batches, sale_items, purchase_order_items | Yes | reorder_level triggers low-stock alert
product_batches | Batch/lot tracking for expiry | id, product_id, batch_no, expiry_date, quantity_remaining, purchase_order_item_id, created_at | products, purchase_order_items | Yes | Enables FEFO deduction + expiry alerts
vendors | Supplier/vendor management | id, name, contact_person, phone, email, address, shop_id, created_at | purchase_orders | Yes
purchase_orders | Purchase (inbound stock) header | id, vendor_id, shop_id, po_date, total_amount, status, created_by, created_at | purchase_order_items, vendors | Yes | status: PENDING¦RECEIVED¦CANCELLED
purchase_order_items | Line items of a purchase order | id, purchase_order_id, product_id, quantity, unit_price, expiry_date, batch_no | purchase_orders, products, product_batches | Yes | Creates product_batch on receive
sales | Sale (outbound) bill header | id, shop_id, sale_date, total_amount, discount, customer_name, created_by, created_at | sale_items | Yes
sale_items | Line items of a sale | id, sale_id, product_id, quantity, unit_price, total_price | sales, products | Yes | Triggers stock_movements on create
stock_movements | Audit log for all stock changes | id, product_id, movement_type (IN¦OUT¦ADJUSTMENT), quantity, reference_id, reference_type, batch_id, created_by, created_at | products, users | Yes | Immutable audit trail
forecast_results | ML demand forecast storage | id, product_id, forecast_date, predicted_quantity, model_version, confidence, created_at | products | Yes | Cached from ML service call
reports | Metadata for generated CSV reports | id, shop_id, report_type, date_range_start, date_range_end, file_url, created_by, created_at | shops, users | Yes | Store S3/local URL of generated CSV

## 🔌 API Reference
🔌 SmartShelf AI — REST API Reference
Module | Method | Endpoint | Description | Auth Reqd | Role Reqd | Request Body (key fields) | Response | Status
Auth | POST | /auth/register | Register new user | No | — | { email, password, name, role } | { id, email, role, token } | 201
Auth | POST | /auth/login | Login and get JWT | No | — | { email, password } | { access_token, user } | 200
Auth | GET | /auth/me | Get current user profile | Yes | Any | — | { id, email, name, role } | 200
Auth | POST | /auth/refresh | Refresh access token | Yes | Any | { refresh_token } | { access_token } | 200
Shops | GET | /shops/:id | Get shop profile | Yes | Any | — | { id, name, address, currency } | 200
Shops | PUT | /shops/:id | Update shop profile | Yes | Admin | { name, address, phone, currency } | Updated shop object | 200
Shops | POST | /shops/:id/members | Add member to shop | Yes | Admin | { user_id, role } | { shop_member } | 201
Categories | GET | /categories | List all categories | Yes | Any | — | [{ id, name }] | 200
Categories | POST | /categories | Create category | Yes | Admin | { name, description } | { id, name } | 201
Categories | PUT | /categories/:id | Update category | Yes | Admin | { name, description } | Updated category | 200
Categories | DELETE | /categories/:id | Delete category | Yes | Admin | — | { message } | 200
Products | GET | /products | List products (with filters) | Yes | Any | ?category_id=&search=&low_stock=true | [{ id, name, sku, quantity, ... }] | 200
Products | POST | /products | Create product | Yes | Admin | { name, sku, category_id, reorder_level, unit, selling_price } | Created product | 201
Products | GET | /products/:id | Get product detail | Yes | Any | — | { ...product, batches } | 200
Products | PUT | /products/:id | Update product | Yes | Admin | { name, selling_price, reorder_level, ... } | Updated product | 200
Products | DELETE | /products/:id | Delete product | Yes | Admin | — | { message } | 200
Vendors | GET | /vendors | List vendors | Yes | Any | — | [{ id, name, contact_person }] | 200
Vendors | POST | /vendors | Create vendor | Yes | Admin | { name, phone, email, address } | Created vendor | 201
Vendors | PUT | /vendors/:id | Update vendor | Yes | Admin | { name, phone, email } | Updated vendor | 200
Vendors | DELETE | /vendors/:id | Delete vendor | Yes | Admin | — | { message } | 200
Purchases | GET | /purchases | List purchase orders | Yes | Any | ?vendor_id=&status= | [{ id, vendor, total, status }] | 200
Purchases | POST | /purchases | Create purchase order | Yes | Admin¦Staff | { vendor_id, items: [{ product_id, qty, unit_price, expiry_date }] } | Created PO + stock updated | 201
Purchases | GET | /purchases/:id | Get PO detail | Yes | Any | — | { ...po, items } | 200
Sales | GET | /sales | List sales | Yes | Any | ?date_from=&date_to= | [{ id, total, sale_date }] | 200
Sales | POST | /sales | Create sale bill | Yes | Admin¦Staff | { items: [{ product_id, quantity, unit_price }], discount, customer_name } | Created sale + stock decremented | 201
Sales | GET | /sales/:id | Get sale detail | Yes | Any | — | { ...sale, items } | 200
Inventory | GET | /inventory/alerts | Get low-stock + expiry alerts | Yes | Any | — | { low_stock: [], expiring_soon: [] } | 200
Inventory | GET | /inventory/movements | Stock movement history | Yes | Any | ?product_id=&type= | [{ movement_type, qty, date }] | 200
Inventory | POST | /inventory/adjust | Manual stock adjustment | Yes | Admin | { product_id, quantity, reason } | Stock movement record | 201
Dashboard | GET | /dashboard/summary | KPI cards data | Yes | Any | — | { total_sales, revenue, low_stock_count, expiring_count } | 200
Dashboard | GET | /dashboard/sales-trend | Weekly sales trend | Yes | Any | ?weeks=4 | [{ week, revenue, count }] | 200
Dashboard | GET | /dashboard/top-products | Top 5 products by revenue | Yes | Any | ?limit=5 | [{ product_name, revenue, qty }] | 200
Reports | POST | /reports/generate | Generate CSV report | Yes | Admin | { report_type: 'sales'¦'inventory'¦'purchases', date_from, date_to } | { file_url } | 201
Reports | GET | /reports | List generated reports | Yes | Any | — | [{ id, type, date_range, file_url }] | 200
ML Forecast | POST | /forecast/train | Trigger model training | Yes | Admin | { product_id? } | { status, model_version } | 200
ML Forecast | POST | /forecast/predict | Get demand forecast | Yes | Any | { product_id, days_ahead: 7 } | { predictions: [{ date, qty }] } | 200
ML Forecast | GET | /forecast/results/:product_id | Get cached forecast | Yes | Any | — | [{ forecast_date, predicted_qty }] | 200

## 🧪 Testing Checklist
🧪 SmartShelf AI — Testing Checklist
# | Test Type | Test Case | Module | Expected Result | Pass/Fail | Day Tested | Notes
1 | Unit | AuthService.register() creates user with hashed password | Auth | User saved with bcrypt hash, not plain text | Pending | 22
2 | Unit | AuthService.login() returns JWT on valid credentials | Auth | Returns { access_token } string | Pending | 22
3 | Unit | AuthService.login() throws 401 on wrong password | Auth | UnauthorizedException thrown | Pending | 22
4 | Unit | ProductsService.create() creates product record | Products | Product with correct fields saved to DB | Pending | 22
5 | Unit | ProductsService.findAll() returns paginated list | Products | Array with pagination metadata | Pending | 22
6 | Unit | SalesService.create() decrements stock quantity | Sales | product quantity decreases by sale quantity | Pending | 22
7 | Unit | SalesService.create() throws 400 if insufficient stock | Sales | BadRequestException: Insufficient stock | Pending | 22
8 | Unit | PurchasesService.create() increments stock quantity | Purchases | product quantity increases by purchase quantity | Pending | 22
9 | Unit | AlertsService returns low-stock products | Inventory | Products below reorder_level in result | Pending | 22
10 | Unit | AlertsService returns expiring products (< 7 days) | Inventory | Batches with expiry_date < today+7 returned | Pending | 22
11 | Unit | ForecastService falls back to rule-based if ML down | ML Forecast | Returns rolling average, no crash | Pending | 22
12 | API | POST /auth/register → 201 with valid payload | Auth | { id, email, role } in response | Pending | 23
13 | API | POST /auth/register → 400 with duplicate email | Auth | 400 Bad Request returned | Pending | 23
14 | API | POST /auth/login → 200 with access_token | Auth | access_token string in body | Pending | 23
15 | API | POST /auth/login → 401 with wrong password | Auth | 401 Unauthorized | Pending | 23
16 | API | GET /products without token → 401 | Products | 401 Unauthorized | Pending | 23
17 | API | POST /products with Admin token → 201 | Products | Product created, id returned | Pending | 23
18 | API | POST /products with Staff token → 403 | Products | 403 Forbidden (Staff can't create) | Pending | 23
19 | API | POST /purchases → stock increases | Purchases | GET /products/:id shows higher qty | Pending | 23
20 | API | POST /sales → stock decreases | Sales | GET /products/:id shows lower qty | Pending | 23
21 | API | POST /sales with qty > stock → 400 | Sales | 400 Bad Request: Insufficient stock | Pending | 23
22 | API | GET /inventory/alerts returns low-stock list | Inventory | Array of products below threshold | Pending | 23
23 | API | GET /dashboard/summary → correct counts | Dashboard | total_sales, revenue match DB aggregates | Pending | 23
24 | API | POST /reports/generate → file_url returned | Reports | CSV file URL in response | Pending | 23
25 | E2E | User can register from /register page | Auth | Redirect to dashboard after register | Pending | 24
26 | E2E | User can login from /login page | Auth | JWT stored, dashboard visible | Pending | 24
27 | E2E | Admin can add a new product via UI | Products | Product appears in product list table | Pending | 24
28 | E2E | Admin can create a vendor | Vendors | Vendor appears in vendor list | Pending | 24
29 | E2E | Admin can create a purchase and stock increases | Purchases | Product qty visibly increases on product page | Pending | 24
30 | E2E | Staff can create a sale bill | Sales | Sale created, stock decreases visible | Pending | 24
31 | E2E | Low-stock alert banner appears when stock < threshold | Inventory | Red alert banner visible on dashboard | Pending | 24
32 | E2E | Expiry alert badge appears on near-expiry product | Inventory | Orange badge on product with <7 day expiry | Pending | 24
33 | E2E | Dashboard charts render with data | Dashboard | Bar chart and line chart visible with data | Pending | 24
34 | E2E | CSV report downloads successfully | Reports | File download triggered, CSV opens correctly | Pending | 24
35 | E2E | Forecast card shows predictions on dashboard | ML Forecast | Forecast table/chart with dates and quantities | Pending | 24
36 | E2E | Staff cannot access admin-only pages | Auth/RBAC | Redirect to /unauthorized or 403 page | Pending | 24

## 🚀 Deployment
🚀 SmartShelf AI — Deployment Checklist
# | Service | Task | Platform | Status | Notes | Target Day
1 | Database | Create Neon PostgreSQL project | Neon | To Do | Free tier, copy connection string | Day 1
2 | Database | Set DATABASE_URL in .env | Local | To Do | postgres://user:pass@host/db | Day 1
3 | Database | Run prisma migrate deploy in production | Neon | To Do | npx prisma migrate deploy | Day 25
4 | Database | Seed production DB with demo data | Neon | To Do | npx prisma db seed | Day 25
5 | Backend | Create Render/Railway service | Render | To Do | Node.js service, connect to GitHub repo | Day 25
6 | Backend | Set all env vars on Render | Render | To Do | DATABASE_URL, JWT_SECRET, ML_SERVICE_URL, CORS_ORIGIN | Day 25
7 | Backend | Deploy NestJS and verify /health endpoint | Render | To Do | GET /health → 200 OK | Day 25
8 | Backend | Enable CORS for Vercel frontend URL | NestJS | To Do | app.enableCors({ origin: process.env.CORS_ORIGIN }) | Day 25
9 | Backend | Verify all API endpoints on production URL | Render | To Do | Use Postman/Insomnia with production base URL | Day 25
10 | ML Service | Create Dockerfile for FastAPI app | Local | To Do | FROM python:3.11-slim, pip install -r requirements.txt | Day 26
11 | ML Service | Test Docker build locally | Local | To Do | docker build -t smartshelf-ml . | Day 26
12 | ML Service | Create Render Docker service | Render | To Do | New service → Docker, connect to GitHub | Day 26
13 | ML Service | Set ML service env vars on Render | Render | To Do | PORT, MODEL_PATH | Day 26
14 | ML Service | Deploy ML service and verify /health | Render | To Do | GET /health → { status: ok } | Day 26
15 | ML Service | Update ML_SERVICE_URL in NestJS env | Render | To Do | Point to production ML URL | Day 26
16 | ML Service | Test /forecast endpoint from NestJS | Render | To Do | POST /forecast returns predictions | Day 26
17 | Frontend | Create Vercel project, connect GitHub | Vercel | To Do | Import repo, set root to /frontend or ./ | Day 27
18 | Frontend | Set NEXT_PUBLIC_API_URL env on Vercel | Vercel | To Do | Points to Render NestJS base URL | Day 27
19 | Frontend | Trigger production build on Vercel | Vercel | To Do | Build logs show no errors | Day 27
20 | Frontend | Test all pages on live Vercel URL | Vercel | To Do | Login, products, purchases, sales, dashboard | Day 27
21 | Frontend | Check mobile responsiveness | Browser | To Do | DevTools → iPhone 14 viewport | Day 27
22 | Final | Test full user journey on production URLs | All | To Do | Register → add product → purchase → sale → dashboard | Day 28
23 | Final | Create demo credentials in seed data | Neon | To Do | admin@demo.com / Demo123! and staff@demo.com / Demo123! | Day 28
24 | Final | Add all production URLs to README.md | GitHub | To Do | Live Demo, API Base URL, ML Service URL | Day 28
25 | Final | GitHub repo: add topics, description, license | GitHub | To Do | Topics: nextjs, nestjs, inventory, typescript | Day 28
26 | Final | Record demo video (Loom/OBS) | Loom | To Do | 3-5 min: login → inventory flow → ML forecast | Day 29
27 | Final | Share on LinkedIn / portfolio site | LinkedIn | To Do | Post with live URL, tech stack, screenshots | Day 30

## ⏱ Time Log
⏱ SmartShelf AI — Daily Time Log
Day | Date | Learn Hrs | Build Hrs | Debug/Commit Hrs | Total Hrs | Main Task Done | Blockers | Notes
1 | Day 1 | 1 | 3 | 0.5 | 4.5
2 | Day 2 |  |  |  | 0
3 | Day 3 |  |  |  | 0
4 | Day 4 |  |  |  | 0
5 | Day 5 |  |  |  | 0
6 | Day 6 |  |  |  | 0
7 | Day 7 |  |  |  | 0
8 | Day 8 |  |  |  | 0
9 | Day 9 |  |  |  | 0
10 | Day 10 |  |  |  | 0
11 | Day 11 |  |  |  | 0
12 | Day 12 |  |  |  | 0
13 | Day 13 |  |  |  | 0
14 | Day 14 |  |  |  | 0
15 | Day 15 |  |  |  | 0
16 | Day 16 |  |  |  | 0
17 | Day 17 |  |  |  | 0
18 | Day 18 |  |  |  | 0
19 | Day 19 |  |  |  | 0
20 | Day 20 |  |  |  | 0
21 | Day 21 |  |  |  | 0
22 | Day 22 |  |  |  | 0
23 | Day 23 |  |  |  | 0
24 | Day 24 |  |  |  | 0
25 | Day 25 |  |  |  | 0
26 | Day 26 |  |  |  | 0
27 | Day 27 |  |  |  | 0
28 | Day 28 |  |  |  | 0
29 | Day 29 |  |  |  | 0
30 | Day 30 |  |  |  | 0
TOTAL | 30 Days | 1 | 3 | 0.5 | 4.5 | Fill in daily to track progress
TARGET |  | 26 | 111.5 | 12 | 149.5 | ~5-6 hrs/day for 30 days

## ⚠️ Risk & Fallback
⚠️ SmartShelf AI — Risk Register & Fallback Plan
# | Risk Category | Risk Description | Probability | Impact | Fallback Plan | Owner/Day
1 | ML/Data | XGBoost model training takes too long or fails to converge | Medium | High | Use rule-based fallback: 7-day rolling average of stock movements for each product. Ship fallback first, ML second. | Day 23 / Self
2 | ML/Data | Online Retail dataset preprocessing is complex | Medium | Medium | Use synthetic data: generate 6-month sales history per product using Python random. Train on that to prove pipeline works. | Day 18 / Self
3 | ML/Data | FastAPI ML service has cold start issues on Render free tier | High | Medium | Add /health ping from NestJS on startup. Show 'forecast loading' state in UI. Cache last forecast in DB. | Day 26 / Self
4 | Backend | Prisma schema becomes too complex with all tables | Medium | High | Start with: users, products, purchases, sales, stock_movements only. Add vendors, batches, forecasts incrementally. | Day 4 / Self
5 | Backend | NestJS circular dependencies between modules | Medium | Medium | Use forwardRef() sparingly. Keep modules loosely coupled. StockMovements should be a separate service injected into Sales/Purchases. | Day 11 / Self
6 | Backend | Stock deduction logic has edge cases (partial batches) | High | High | Implement simple total-quantity deduction first (no FEFO). Add FEFO batch logic only after basic sale billing works. | Day 13 / Self
7 | Frontend | UI takes too long to build with custom designs | High | Medium | Use only ShadCN pre-built components (Table, Dialog, Card, Badge). Zero custom CSS. Tailwind utilities only. | Day 6 / Self
8 | Frontend | React Hook Form + Zod integration issues | Low | Medium | Use RHF v7 zodResolver. Copy patterns from official RHF docs. Test each form in isolation before integration. | Day 3 / Self
9 | Deployment | Backend deployment fails due to env var mismatch | Medium | High | Keep a .env.production file template in repo (no secrets). Test deployment script locally with Docker before pushing. | Day 25 / Self
10 | Deployment | Render/Railway free tier sleeps after inactivity | High | Medium | Use Render cron job or external uptime monitor (cron-job.org) to ping /health every 14 minutes. | Day 27 / Self
11 | Deployment | Vercel build fails due to TypeScript errors | Medium | Medium | Run npm run build locally before pushing. Fix all TS errors. Set strictNullChecks: true from Day 1. | Day 27 / Self
12 | Time | Week 3 ML + Dashboard takes longer than planned | High | Medium | Cut advanced charts (keep only 1 line + 1 bar). Ship basic forecast as text-only table first, add chart later. | Day 21 / Self
13 | Time | Testing week (Week 4) expands unexpectedly | Medium | Medium | Write unit tests in parallel during Week 1-3 (one test file per module). Don't leave all testing to Week 4. | Day 22 / Self
14 | Time | README + portfolio polish takes more than 1 day | Low | Low | Use a README template. Take screenshots as you build each feature. Don't wait until Day 28. | Day 30 / Self
15 | Security | JWT secret leaked to GitHub | Low | Critical | Use .env files, never commit secrets. Add .env to .gitignore on Day 1. Use GitHub Secrets for CI/CD. | Day 1 / Self

## 🔮 Deferred Features
🔮 SmartShelf AI — Post-MVP Deferred Features
# | Feature | Category | Complexity | Business Value | Tech Stack Hint | Target Phase
1 | Customer segmentation (RFM analysis) | ML | High | High | Pandas + KMeans/DBSCAN, new /segments endpoint in FastAPI | v1.1 - Post MVP
2 | Association rule mining (Market basket) | ML | High | Medium | mlxtend FP-Growth, recommend complementary products | v1.1 - Post MVP
3 | Anomaly detection for sales/inventory | ML | High | High | Isolation Forest or Z-score on daily sales time series | v1.2
4 | Payment gateway integration | Payments | High | High | Razorpay or Stripe SDK, webhook for payment confirmation | v1.1 - Post MVP
5 | GST / tax filing export | Compliance | Medium | High | GST GSTR-1 format CSV/JSON, Indian tax calculation | v2.0
6 | Advanced PDF reports (with charts) | Reports | Medium | Medium | WeasyPrint or Puppeteer PDF generation | v1.1 - Post MVP
7 | WhatsApp / SMS low-stock alerts | Notifications | Medium | High | Twilio SMS or WhatsApp Business API | v1.1 - Post MVP
8 | Email notifications (SMTP) | Notifications | Low | Medium | Nodemailer in NestJS, daily digest email | v1.1 - Post MVP
9 | Mobile app (React Native / Flutter) | Mobile | Very High | High | Expo React Native or Flutter, same NestJS backend | v2.0
10 | Progressive Web App (PWA) | Frontend | Low | Medium | next-pwa, service worker, offline mode | v1.1 - Post MVP
11 | Multi-location / multi-branch support | Architecture | High | High | shop_locations table, location-based stock queries | v2.0
12 | SaaS billing (subscription tiers) | Business | Very High | High | Stripe Billing, plan-based feature gating | v2.0
13 | Redis caching layer | Performance | Medium | Medium | ioredis, cache dashboard queries, forecast results | v1.2
14 | Redis job queues (BullMQ) | Performance | Medium | Medium | BullMQ for async report generation and ML training jobs | v1.2
15 | Kubernetes deployment | DevOps | Very High | Low | K8s manifests, horizontal pod autoscaling | v3.0
16 | Advanced CI/CD pipeline | DevOps | Medium | Medium | GitHub Actions: lint, test, build, deploy on merge to main | v1.1 - Post MVP
17 | Customer purchase history portal | Feature | Medium | Medium | Customer-facing portal, order history, invoices | v2.0
18 | Supplier portal / vendor self-service | Feature | High | Medium | Vendor login, PO confirmation, delivery tracking | v2.0
19 | Barcode scanner integration | Feature | Medium | High | QuaggaJS or ZXing for camera-based barcode scan | v1.1 - Post MVP
20 | Dark mode UI | Frontend | Low | Low | next-themes, Tailwind dark: variants | v1.1 - Post MVP
21 | Internationalization (i18n) | Frontend | Medium | Medium | next-intl, multi-language support (Hindi, Tamil, etc.) | v2.0
22 | Data export to Google Sheets | Integration | Medium | Medium | Google Sheets API v4, scheduled sync | v2.0